## Sheet1
System overview
CODE | Module | Functions | Start Date | End Date | Status
REQ_1 | User Management | Add/Update/Delete Users | 17/1/2015 | 30/1/2015
Register Account
REQ_2 | Role Management | Add/Update/Delete Roles | 17/1/2015 | 30/1/2015
Assign Role to Users
REQ_3 | Sales | Add/Update/Delete customer information | 17/1/2015 | 2015-07-02 |  | First Payment (30%)
REQ_4 | Document & Operations | Manage services information for a specific customer | 31/1/2015 | 13/2/2015
REQ_5 | Trucking & Delivery | Manage package information | 14/2/2015 | 21/2/2015
REQ_6 | Accounting | Report (Not very clear at the moment) | 22/2/2015 | 2015-07-03
Acceptance Test: | 15/3 -> 21/3(Final Payment)
Warranty: | 22/3 -> 4/4
Plan for requirment collecting
30/1/2015 | Verify user interface for the whole system
User Management
Role Management
Sales
2015-06-02 | Document & Operations
Trucking & Delivery
13/2/2015 | Accounting
27/2/2015 | Review system

## Sheet2
Trucking | Fee details
DEBIT | finish ui + excel |  | 2015-03-02
Trans | finish UI + excel |  | 2015-03-03 | Accounting fee tables | Workflow | Profit Load UI | Debit UI | Trans UI
Profit load | UI | 2015-03-05 | 2015-03-04 | Excel
| Excel |  |  | Nhap hang | Xuat hang
accounting fee tables
workflow (detail)

## Sheet4
1 | localization handler
2 | i18n for js
3 | change gourp main wro.xml
4 | customer added by who?
5 | uniques validation & others validation
Input vietnamese
email sending
6 | Is deleted
7 | configuration | some are not editable
date time format on UI
format number
| find whole object at manager class | Customer | Docs
table relationship
cascade remove
filter for each list
indexing
| disable customer code | don't allow to access
notification on editing approved values
database size modification
bug configuration edit form
inscrease tomcat memory Pergem
date formmater
tong chi phi theo tung loai
datetime format on UI
UI (reponsive table)

## Sheet3
1 | Chi phi Theo tung lo hang , tung khach hang theo thoi gian ( vi du thang 1, or 3thang) …
*Thoi gian tinh bang field nao
Thông tin khách hàng
Bảng chi phí
| STT | JobFile | Loại dịch vụ | Loại chi phí | Tên chi phí | Ngày giao hàng
- DOanh thu Theo tung lo hang , tung khach hang theo thoi gian ( vi du thang 1, or 3thang) …
| - Tong hop san luong va chi phi theo tung NHA THAU , theo thang or theo khach hang, theo job file or theo thoi gian minh can con |  |  | san luong? Doanh thu?
- San luong cac lo hang cua tung khach hang , hang thang or theo thoi gian minh can chon
- San luong tong hop cua tung loai hinh dich vu hang thang or theo thoi gian minh can chon

## Sheet5
select2 | add new when not match
datatable
nestedtable
pnotify
reflowtable
boostwatch
webjars
datepicker
date-timepicker
fontawesome